## Sheet1
Task | Estimate (hours) | Complete By | Status
Create database/table in dev environmnent | 0.25 | 2015-10-26 | Completed
Add Sample Data | 0.5 | 2015-10-26 | Completed
Import DB as deployable project | 0.25 | 2015-10-26 | Completed
Initialize New Visual Studio Website | 0.25 | 2015-10-26 | Completed
Create Entity Data Model | 0.25 | 2015-10-27 | Completed
Create MVC Scaffolded Item | 0.25 | 2015-10-27 | Completed
Modify "Listing" look and feel | 0.5 | 2015-10-27 | Not Started
Create RESTful service for contact detail | 0.25 | 2015-10-27 | Not Started
Add client-side code for contact detail | 2 | 2015-10-28 | Not Started
Modify "New" look and feel | 0.5 | 2015-10-29 | Not Started
Add client-side "Cancel" warning to "New" | 0.5 | 2015-10-29 | Not Started
Implement data storage for "New" | 0.25 | 2015-10-29 | Not Started
Modify "Add" look and feel | 0.5 | 2015-10-29 | Not Started
Add client-side "Cancel" warning to "Add" | 0.5 | 2015-10-30 | Not Started
Implement data storage for "Add" | 0.25 | 2015-10-30 | Not Started
Add client-side "Cancel" warning to "Delete" | 0.5 | 2015-10-30 | Not Started
Implement data storage "Delete" | 0.25 | 2015-10-30 | Not Started
Implement RESTful service for contact filter | 2 | 2015-10-31 | Not Started
Add client-side script for dynamic filtering | 4 | 2015-10-31 | Not Started
Create deployment package | 2 | 2015-10-31 | Not Started
Total: | 15.75